## Changes
short_description | long_description | change_type | change_category | implementation_steps | validation_steps | rollback_plan | planned_window | impacted_services | complexity
Update help documentation for user profile section | Refresh user-facing help documentation to reflect recent UI changes in the profile management section. This is a documentation-only change with no code modifications. | standard | configuration | 1. Update markdown documentation files ¦ 2. Review with UX team ¦ 3. Publish to help center ¦ 4. Notify support team | Documentation reviewed by product team ¦ Screenshots updated ¦ Links verified ¦ Grammar and spelling checked | Restore previous documentation version from git history. Takes 2 minutes. No system impact. | 2024-03-25T14:00:00Z | documentation-service | low
Add logging for API request failures | Add additional debug logging statements to capture details of failed API requests for better troubleshooting. No functional changes, only observability improvements. | standard | configuration | 1. Add log statements in error handlers ¦ 2. Deploy to staging for validation ¦ 3. Deploy to production ¦ 4. Verify logs in CloudWatch | Code review completed by 2 engineers ¦ Tested in development environment ¦ Log format validated ¦ No performance impact measured | Remove logging statements via deployment rollback. Automated rollback available. Takes 3 minutes. | 2024-03-26T11:00:00Z | api-gateway | low
Update email notification template footer | Change company address and support email in email notification template footer to reflect office relocation. Template-only change affecting future emails. | standard | configuration | 1. Update email template in CMS ¦ 2. Send test emails ¦ 3. Verify rendering across email clients ¦ 4. Activate new template | Template tested in Gmail, Outlook, Apple Mail ¦ Mobile rendering verified ¦ Links tested ¦ Legal team approved | Revert to previous template version in CMS. Instant rollback available. No system restart required. | 2024-03-27T10:00:00Z | email-service | low
Increase session timeout from 15 to 30 minutes | Extend user session timeout to reduce re-authentication frequency based on user feedback. Configuration change only, no code modifications required. | standard | configuration | 1. Update session timeout config parameter ¦ 2. Deploy configuration change ¦ 3. Monitor active sessions ¦ 4. Verify timeout behavior | Config change tested in staging ¦ Security team approved ¦ No impact on existing sessions ¦ Timeout behavior validated | Revert configuration to 15 minutes. Change takes effect immediately. No service restart needed. | 2024-03-27T09:00:00Z | auth-service | low
Add new FAQ section to help center | Create new frequently asked questions section covering billing and payment topics. Content addition only, no system changes required. | standard | configuration | 1. Draft FAQ content ¦ 2. Review with support and billing teams ¦ 3. Add to help center CMS ¦ 4. Publish and announce | Content approved by subject matter experts ¦ Formatting verified ¦ Search functionality tested ¦ Mobile view checked | Remove FAQ section from CMS. Instant rollback. No technical dependencies. | 2024-03-28T13:00:00Z | documentation-service | low
Update CDN cache TTL for images to 24 hours | Increase CloudFront cache time-to-live for static image assets from 1 hour to 24 hours to reduce origin server load and improve performance. Does not affect dynamic content. | standard | configuration | 1. Update CloudFront distribution cache behavior ¦ 2. Invalidate current cached images ¦ 3. Monitor origin request rate ¦ 4. Verify image loading performance | Cache behavior tested in test distribution ¦ Origin load impact modeled ¦ No user-facing changes expected ¦ Invalidation procedure verified | Revert CloudFront cache TTL to 1 hour. Takes 2 minutes. Previous cache entries expire naturally. | 2024-03-29T04:00:00Z | cdn-cloudfront | low
Add monitoring alert for high memory usage | Configure CloudWatch alarm to alert operations team when application server memory usage exceeds 85%. Observability improvement with no functional changes. | standard | configuration | 1. Create CloudWatch alarm ¦ 2. Configure SNS notification ¦ 3. Test alarm trigger ¦ 4. Document in runbook | Alarm threshold validated against historical data ¦ SNS topic tested ¦ Notification routing verified ¦ False positive rate acceptable | Delete CloudWatch alarm. Immediate removal. No impact on monitored systems. | 2024-03-29T10:00:00Z | monitoring-cloudwatch | low
Update product image thumbnails | Replace product catalog thumbnail images with higher resolution versions for better display on retina screens. Asset replacement only, no code changes. | standard | configuration | 1. Upload new thumbnail images to S3 ¦ 2. Update image URLs in database ¦ 3. Clear CDN cache ¦ 4. Verify image quality | Image quality reviewed by design team ¦ File sizes optimized ¦ URLs validated ¦ Mobile rendering checked | Restore previous thumbnail images from S3 backup. Instant rollback. Update database URLs back. | 2024-03-30T12:00:00Z | product-catalog,cdn-cloudfront | low
Change default sort order to newest first | Update default sort order for search results to show newest items first instead of relevance. User interface preference change, no backend logic changes. | standard | configuration | 1. Update default sort parameter in UI ¦ 2. Deploy frontend change ¦ 3. Verify sort behavior ¦ 4. Monitor user engagement | Sort logic tested with various data sets ¦ User research supports change ¦ Performance impact minimal ¦ Accessibility maintained | Revert to relevance-based sorting via configuration change. Immediate rollback available. | 2024-03-30T11:00:00Z | search-ui | low
Add new language option: Spanish | Add Spanish language translations to application interface to support expanded market. Translation files only, no code modifications required. | standard | configuration | 1. Add Spanish translation files ¦ 2. Update language selector ¦ 3. Deploy to staging ¦ 4. Test all translated strings ¦ 5. Deploy to production | Translations reviewed by native Spanish speakers ¦ All UI strings covered ¦ Character encoding verified ¦ Right-to-left text not applicable | Remove Spanish language option from selector. Translation files can remain. Takes 2 minutes. | 2024-03-31T10:00:00Z | localization-service | low
Update copyright year in footer to 2024 | Annual copyright year update in website footer. Simple text change affecting all pages. | standard | configuration | 1. Update footer component ¦ 2. Deploy to production ¦ 3. Verify on multiple pages | Visual inspection completed ¦ Footer displays correctly across browsers | Revert footer change via git rollback. Takes 2 minutes. | 2024-01-02T10:00:00Z | web-frontend | low
Add social media links to contact page | Add company social media profile links (Twitter, LinkedIn, Facebook) to contact us page. Content addition, no functional changes. | standard | configuration | 1. Add social media icons and links ¦ 2. Deploy to staging ¦ 3. Verify links ¦ 4. Deploy to production | All links tested and verified ¦ Icons display correctly ¦ Mobile responsive | Remove social media section. Instant rollback via deployment. | 2024-04-01T14:00:00Z | web-frontend | low
Update terms of service effective date | Update the effective date on terms of service page to reflect latest legal review. Text change only. | standard | configuration | 1. Update TOS page ¦ 2. Get legal approval ¦ 3. Deploy to production | Legal team approved ¦ Date format consistent | Revert to previous date. Immediate rollback. | 2024-04-02T09:00:00Z | legal-pages | low
Add new dashboard widget for sales metrics | Add read-only dashboard widget displaying daily sales metrics for management team. Data visualization only, no write operations. | standard | configuration | 1. Create widget component ¦ 2. Connect to analytics API ¦ 3. Deploy to dashboard ¦ 4. Grant access to management users | Widget tested with real data ¦ Performance acceptable ¦ Refresh rate appropriate ¦ Access controls verified | Remove widget from dashboard configuration. Immediate rollback. No data dependencies. | 2024-04-03T11:00:00Z | dashboard-service | low
Deploy bug fix release v2.8.1 | Deploy patch release containing fixes for 5 non-critical bugs reported by users. Includes fixes for display issues, minor calculation errors, and performance improvements. | standard | deployment | 1. Deploy to staging environment ¦ 2. Run full regression test suite ¦ 3. Perform smoke testing ¦ 4. Deploy to production with rolling restart ¦ 5. Monitor error rates | All unit tests passing (98% coverage) ¦ Integration tests passed ¦ Manual QA completed ¦ Performance benchmarks acceptable ¦ Security scan clean | Automated rollback to v2.8.0 via Kubernetes deployment revision. Estimated time: 5 minutes. Rollback tested in staging. | 2024-04-04T07:00:00Z | api-service,web-service | medium
Add database index on orders.customer_id column | Create database index to optimize customer order lookup queries which are currently causing slow page loads. Index will be created concurrently to avoid locking. | standard | database | 1. Create index concurrently on production replica ¦ 2. Measure query performance improvement ¦ 3. Create index on primary database ¦ 4. Update query plans ¦ 5. Monitor database performance | Index creation tested on staging database ¦ Query performance improved by 70% ¦ No table locking required ¦ Index size acceptable (500MB) ¦ Replica lag monitored | Drop index if performance degrades or disk space issues arise. Drop operation takes 30 seconds. Queries will use existing indexes. | 2024-04-05T05:00:00Z | rds-orders-database,order-api | medium
Update Node.js runtime from v16 to v18 | Upgrade Node.js runtime version for improved performance and security. All dependencies verified compatible. Requires application restart. | standard | infrastructure | 1. Update Docker base image ¦ 2. Run compatibility tests ¦ 3. Deploy to staging ¦ 4. Performance testing ¦ 5. Deploy to production with rolling restart | All dependencies compatible with Node 18 ¦ Performance tests show 15% improvement ¦ Memory usage stable ¦ Security vulnerabilities addressed | Rollback Docker image to Node 16 version. Requires redeployment. Estimated time: 8 minutes. | 2024-04-06T06:00:00Z | api-service,worker-service,web-service | medium
Add new payment_gateway_id column to orders table | Database schema change to support multiple payment gateways. Adds new column and migrates existing orders to default gateway. Affects core transaction processing. | normal | database | 1. Add column with default value ¦ 2. Backfill existing records ¦ 3. Deploy application code to use new column ¦ 4. Verify data integrity ¦ 5. Monitor payment processing | Schema change tested on production copy ¦ Data migration script validated ¦ Application changes tested in staging ¦ Rollback procedure verified | Rollback application deployment to ignore new column. Column can remain in database. Restore from backup if data corruption. Estimated time: 15 minutes. | 2024-04-07T03:00:00Z | rds-orders-database,payment-service,order-api,checkout-service | high
Deploy v3.0.0 with refactored authentication system | Major version deployment with completely refactored authentication system. Migrates from session-based to JWT tokens. All existing user sessions will be invalidated requiring re-login. | normal | deployment | 1. Deploy new auth service ¦ 2. Run session migration script ¦ 3. Enable JWT validation ¦ 4. Invalidate old sessions ¦ 5. Monitor authentication success rate ¦ 6. Support team ready for user inquiries | New auth system extensively tested ¦ Load testing passed ¦ Security audit completed ¦ Mobile app compatibility verified ¦ Session migration tested | Rollback to v2.x requires restoring session-based auth and invalidating JWT tokens. Complex rollback taking 20-30 minutes. Session data backup available. | 2024-04-08T02:00:00Z | auth-service,api-gateway,web-frontend,mobile-app-backend,session-store | high
Emergency patch for critical security vulnerability CVE-2024-12345 | Emergency deployment to patch critical remote code execution vulnerability in authentication library. Immediate deployment required per security team. Limited testing time available. | emergency | deployment | 1. Apply security patch immediately ¦ 2. Restart all affected services ¦ 3. Verify patch effectiveness ¦ 4. Monitor for exploitation attempts ¦ 5. Coordinate with security team | Patch verified by security team ¦ Functionality smoke tested in isolated environment ¦ Exploit no longer reproducible | Cannot rollback - would re-expose critical security vulnerability. Must fix forward if issues arise. Emergency hotfix team on standby. | 2024-04-09T16:30:00Z | auth-service,api-gateway,web-frontend,mobile-app-backend,admin-portal | high